## Medusa Hill Feast - Time line
Task Name | Start Date | End Date | Duration (Days)
Get start with Unity (Creating Starting UI) | 2017-09-10 | 2017-09-17 | 7
Map create and add image movement | 2017-09-17 | 2017-09-22 | 5
Create image animation in Unity | 2017-09-22 | 2017-09-24 | 2
Write dialog | 2017-09-24 | 2017-09-25 | 1
Add dialog and character image for dialog into Unity project | 2017-09-25 | 2017-09-30 | 5
Design detail on cooking system | 2017-10-01 | 2017-10-02 | 1
Produce controller, and add item system into project | 2017-10-01 | 2017-10-13 | 12
Cooking system design and import | 2017-10-12 | 2017-10-21 | 9
Friendship system design and import | 2017-10-22 | 2017-10-28 | 6
Theme music add, and sound effect | 2017-10-27 | 2017-10-31 | 4
QA Testing and writing documentations | 2017-10-29 | 2017-11-06 | 8
Improve all the imported resource and code fight system if applicable | 2017-11-05 | 2017-11-18 | 13
Prepare for presentation, and improve the art work | 2017-11-19 | 2017-11-25 | 6
Presentation | 2017-11-26 | 2017-12-02 | 6
Formulas:
End Date = IF(ISBLANK([Duration (Days)]),"",[Duration (Days)]+[Start Date])